## Schedule
FIGURINHA TRADER — Ultra-Detailed Development Schedule
Apr 4 → Apr 20, 2026 • 17 days • ~105h • Submit deadline: Apr 20
Priority: 🔴 CRITICAL ¦ 🟠 HIGH ¦ 🟡 MEDIUM ¦ 🟢 LOW — Status: ☐ To do ¦ ⏳ In progress ¦ ✅ Done
# | Date | Block | Phase | Specific Task | Files / Components | Technology / Lib | h | Status | Model | Skills Used | Executed by
1a | Apr 4 Sat | Morning | SETUP | Create Expo project with TypeScript | / (raiz) — app.json, tsconfig.json, package.json, .env, .gitignore | npx create-expo-app figurinha-trader --template blank-typescript | 2h | ☐ | Sonnet | plugin-structure, command-development, agent-development, mcp-integration, gws-drive | Code
1b | Apr 4 Sat | Morning | SETUP | Configure GitHub repo and folder structure | src/screens/, src/components/, src/hooks/, src/lib/, src/types/, src/store/, assets/ | git init, gh repo create | 1h | ☐ | Haiku | plugin-structure, gws-drive, gws-docs, recipe-organize-drive-folder | Code
1c | Apr 4 Sat | Afternoon | SETUP | Create Supabase project (free tier) and configure .env | .env: SUPABASE_URL, SUPABASE_ANON_KEY, SUPABASE_SERVICE_KEY | supabase.com → New Project → figurinha-trader | 1h | ☐ | Haiku | gws-drive, gws-docs, mcp-integration, recipe-create-shared-drive | Code
1d | Apr 4 Sat | Afternoon | SETUP | Create Apple Developer account + Google Play Console | developer.apple.com (US$99/year) + play.google.com/console (US$25 one-time) | Apple Developer Program, Google Play Console | 1h | ☐ | Haiku | gws-chat-send, gws-gmail-send, recipe-send-team-announcement | Code
1e | Apr 4 Sat | Afternoon | SETUP | Install core project dependencies | package.json atualizado | expo-router, @supabase/supabase-js, zustand, react-hook-form, zod | 1h | ☐ | Haiku | gws-sheets, recipe-create-task-list, recipe-review-overdue-tasks | Code
1f | Apr 4 Sat | Evening | SETUP | Configure AWS EC2 (Free Tier) — provision instance and deploy N8N via Docker | ~/.ssh/ocloud_figurinha (SSH key) ¦ docker-compose.yml (N8N) ¦ fixed public IP on AWS | cloud.oracle.com → VM.Standard.A1.Flex ¦ Docker + docker compose up -d ¦ port 5678 open | 1h | ☐ | Sonnet | schedule, gws-workflow, mcp-integration, recipe-create-task-list, gws-chat-send, agent-development | Cowork
2a | Apr 5 Sun | Morning | SETUP | Create database tables: profiles, albums, figurinhas | supabase/migrations/001_core.sql | Supabase Dashboard → SQL Editor ¦ tables with UUID, timestamps, RLS | 2h | ☐ | Sonnet | docx, gws-docs, gws-sheets, recipe-generate-report-from-sheet, recipe-backup-sheet-as-csv | Code
2b | Apr 5 Sun | Morning | SETUP | Create tables: colecoes, itens_colecao, wishlist | supabase/migrations/002_colecao.sql | FK to profiles and figurinhas; indexes on (user_id, figurinha_id) | 1h | ☐ | Sonnet | docx, gws-docs, gws-sheets, recipe-generate-report-from-sheet | Code
2c | Apr 5 Sun | Afternoon | SETUP | Create tables: anuncios, conversas, mensagens | supabase/migrations/003_trocas.sql | Realtime enabled on messages; RLS: only conversation parties read | 2h | ☐ | Sonnet | docx, gws-docs, recipe-generate-report-from-sheet | Code
2d | Apr 5 Sun | Afternoon | SETUP | Create tables: encontros, confirmacoes, avaliacoes, pins_verificados | supabase/migrations/004_social.sql | Correct FKs; trigger auto-update avg_rating in profiles | 1h | ☐ | Sonnet | docx, gws-docs, recipe-generate-report-from-sheet, gws-drive-upload | Code
3a | Apr 6 Mon | Morning | SETUP | Configure authentication: Email, Google OAuth, Apple Sign In | src/lib/supabase.ts, src/lib/auth.ts | @supabase/supabase-js, expo-auth-session, expo-crypto | 2h | ☐ | Sonnet | gws-drive, gws-docs, docx, plugin-structure | Code
3b | Apr 6 Mon | Morning | SETUP | Create Design System: colors, typography, spacing | src/theme/colors.ts, src/theme/typography.ts, src/theme/spacing.ts | TypeScript constants — no external UI lib | 1h | ☐ | Haiku | canvas-design, frontend-design, theme-factory, excalidraw-diagram, gws-docs, recipe-create-presentation, gws-sheets, valyu-best-practices | Code
3c | Apr 6 Mon | Afternoon | SETUP | Create base components: Button, Input, Card, Avatar, Badge, LoadingSpinner | src/components/ui/Button.tsx, Input.tsx, Card.tsx, Avatar.tsx, Badge.tsx | React Native core + StyleSheet — no external lib | 2h | ☐ | Sonnet | frontend-design, web-artifacts-builder, theme-factory, canvas-design, valyu-best-practices, recipe-create-presentation | Code
3d | Apr 6 Mon | Afternoon | SETUP | Configure navigation: Bottom Tabs + Stack per tab | src/app/_layout.tsx, src/app/(tabs)/_layout.tsx e 5 tabs | expo-router v3 (file-based routing) | 1h | ☐ | Sonnet | frontend-design, web-artifacts-builder, canvas-design, excalidraw-diagram | Code
4a | Apr 7 Tue | Morning | COLLECTION | Collection screen: sticker list with filters | src/app/(tabs)/colecao/index.tsx, src/components/FigurinhaCard.tsx | FlatList with FlashList (@shopify/flash-list) for performance | 3h | ☐ | Sonnet | frontend-design, web-artifacts-builder, claude-d3js-skill, canvas-design, recipe-create-presentation | Code
4b | Apr 7 Tue | Morning | COLLECTION | Logic to mark have/missing/duplicate with quantity | src/hooks/useColecao.ts, src/store/colecaoStore.ts | Zustand for local state; Supabase upsert on itens_colecao | 2h | ☐ | Sonnet | gws-sheets, recipe-log-deal-update, gws-workflow | Code
4c | Apr 7 Tue | Afternoon | COLLECTION | Progress bar and basic stats (% complete, X missing) | src/components/ColecaoProgress.tsx, src/app/(tabs)/colecao/stats.tsx | Animated.View for bar; Supabase count(*) query | 2h | ☐ | Haiku | frontend-design, claude-d3js-skill, canvas-design, gws-sheets-append | Code
5a | Apr 8 Wed | Morning | COLLECTION | Implement AI scan with Google ML Kit (text recognition) | src/app/(tabs)/colecao/scan.tsx, src/lib/mlkit.ts | react-native-vision-camera + @react-native-ml-kit/text-recognition | 3h | ☐ | Sonnet | webapp-testing, browser-use, playwright-skill, gws-forms, recipe-collect-form-responses | Code
5b | Apr 8 Wed | Morning | COLLECTION | Open pack mode: register 7 stickers in quick sequence | src/app/(tabs)/colecao/pacote.tsx | Screen flow with swipe confirm; batch insert in Supabase | 2h | ☐ | Sonnet | frontend-design, web-artifacts-builder, canvas-design, gws-docs | Code
5c | Apr 8 Wed | Afternoon | COLLECTION | Free tier gate (30 scans/day): daily counter in Supabase | src/hooks/useScanLimit.ts — tabela scan_logs (user_id, date, count) | Supabase RPC to increment and check limit | 2h | ☐ | Haiku | gws-sheets, recipe-log-deal-update, gws-workflow | Code
6a | Apr 9 Thu | Morning | TRADES | Create trade listing screen | src/app/(tabs)/trocas/novo.tsx, src/hooks/useAnuncio.ts | react-hook-form + zod for validation; insert in anuncios | 2h | ☐ | Sonnet | frontend-design, web-artifacts-builder, persona-sales-ops, gws-forms, gws-docs, recipe-email-drive-link | Code
6b | Apr 9 Thu | Morning | TRADES | Listings feed with search by number/player/country | src/app/(tabs)/trocas/index.tsx, src/components/AnuncioCard.tsx | FlashList; Supabase full-text search on figurinhas | 2h | ☐ | Sonnet | frontend-design, web-artifacts-builder, recipe-email-drive-link, gws-drive-upload, claude-d3js-skill, persona-sales-ops | Code
6c | Apr 9 Thu | Afternoon | TRADES | Featured badge for premium listings (sorting and visual) | src/components/AnuncioCard.tsx (prop: featured), src/hooks/usePremium.ts | ORDER BY is_premium DESC in query; visual badge on card | 1h | ☐ | Haiku | canvas-design, theme-factory, gws-docs | Code
6d | Apr 9 Thu | Afternoon | TRADES | Wishlist: add/remove wanted stickers, display on profile | src/app/(tabs)/trocas/wishlist.tsx, src/hooks/useWishlist.ts | Supabase upsert on wishlist; heart icon on FigurinhaCard | 2h | ☐ | Haiku | frontend-design, recipe-create-task-list, gws-tasks, gws-chat-send | Code
7a | Apr 10 Fri | Morning | TRADES | Real-time chat: conversation screen | src/app/chat/[conversaId].tsx, src/components/MessageBubble.tsx | Supabase Realtime (channel subscribe on messages); inverted FlatList | 3h | ☐ | Sonnet | frontend-design, web-artifacts-builder, gws-chat-send, gws-chat, gws-gmail, recipe-create-gmail-filter | Code
7b | Apr 10 Fri | Morning | TRADES | Active conversations list | src/app/(tabs)/trocas/mensagens.tsx, src/components/ConversaCard.tsx | Supabase query with JOIN on profiles for other user name/avatar | 2h | ☐ | Haiku | frontend-design, web-artifacts-builder, gws-chat, gws-chat-send | Code
7c | Apr 10 Fri | Afternoon | TRADES | Start conversation from a listing | src/hooks/useChat.ts — criar ou reusar conversa existente entre dois users | Supabase upsert on conversas with UNIQUE(user1_id, user2_id, anuncio_id) | 2h | ☐ | Haiku | recipe-create-gmail-filter, recipe-label-and-archive-emails, gws-gmail-watch, gws-workflow | Code
8a | Apr 11 Sat | Morning | SEARCH | Profile search by name/@username | src/app/(tabs)/busca/index.tsx, src/components/PerfilCard.tsx | Supabase ilike on profiles.username and profiles.full_name; debounce 300ms | 2h | ☐ | Sonnet | frontend-design, web-artifacts-builder, gws-people, gws-sheets-read, persona-exec-assistant | Code
8b | Apr 11 Sat | Morning | SEARCH | Sticker search: 'who has #347?' | src/app/(tabs)/busca/por-figurinha.tsx | JOIN itens_colecao + profiles WHERE figurinha_id = X AND tem = true | 2h | ☐ | Sonnet | frontend-design, web-artifacts-builder, claude-d3js-skill, gws-sheets, recipe-generate-report-from-sheet | Code
8c | Apr 11 Sat | Afternoon | SEARCH | Location search (radius in km, free=city, premium=custom radius) | src/app/(tabs)/busca/por-localizacao.tsx, src/lib/geo.ts | Supabase PostGIS extension; ST_DWithin for radius; expo-location | 2h | ☐ | Sonnet | frontend-design, web-artifacts-builder, gws-drive, gws-sheets, recipe-find-large-files | Code
8d | Apr 11 Sat | Afternoon | SEARCH | Automatic suggestion of compatible profiles (bilateral match) | src/hooks/useMatchSugestoes.ts — Supabase RPC match_bilateral(user_id) | SQL: user A has what B needs AND B has what A needs | 2h | ☐ | Sonnet | gws-sheets, recipe-log-deal-update, persona-sales-ops | Code
9a | Apr 12 Sun | Morning | MAPA | Map screen with OpenFreeMap + MapLibre React Native | src/app/(tabs)/mapa/index.tsx, src/lib/mapa.ts | @maplibre/maplibre-react-native; tiles: https://tiles.openfreemap.org/styles/liberty | 3h | ☐ | Sonnet | frontend-design, web-artifacts-builder, excalidraw-diagram, canvas-design, gws-sheets | Code
9b | Apr 12 Sun | Morning | MAPA | Meeting pins on map (blue=user, gold=venue) | src/components/mapa/PinEncontro.tsx, src/components/mapa/PinVerificado.tsx | ShapeSource + SymbolLayer from MapLibre; custom SVG icons | 2h | ☐ | Sonnet | canvas-design, theme-factory, gws-drive-upload | Code
9c | Apr 12 Sun | Afternoon | MAPA | Create meeting point (premium only): form with address + OpenCage geocoding | src/app/(tabs)/mapa/novo-encontro.tsx, src/lib/geocoding.ts | OpenCage API (2,500 req/day free); react-hook-form + zod | 2h | ☐ | Sonnet | frontend-design, recipe-schedule-recurring-event, gws-calendar-insert, gws-calendar, gws-docs | Code
9d | Apr 12 Sun | Afternoon | MAPA | 'I'll attend' button + confirmed list (premium sees full list) | src/hooks/useEncontro.ts — upsert em confirmacoes_encontro | Realtime on counter; premium gate to see names list | 1h | ☐ | Haiku | recipe-batch-invite-to-event, gws-calendar-insert, gws-calendar, gws-chat-send, gws-gmail-send | Code
10a | Apr 13 Mon | Morning | SOCIAL | Public profile screen (own + others) | src/app/perfil/[userId].tsx, src/components/perfil/PerfilHeader.tsx, PerfilStats.tsx | Supabase single row with JOIN on stats; expo-image for avatar | 3h | ☐ | Sonnet | frontend-design, web-artifacts-builder, persona-exec-assistant, gws-people, gws-sheets-read, canvas-design | Code
10b | Apr 13 Mon | Morning | SOCIAL | Collector ranking by city (% complete + trades) | src/app/(tabs)/busca/ranking.tsx, src/components/RankingCard.tsx | Supabase VIEW ranking_usuarios with % calc and trade count | 2h | ☐ | Haiku | frontend-design, claude-d3js-skill, recipe-generate-report-from-sheet, gws-sheets, gws-sheets-read, persona-sales-ops | Code
10c | Apr 13 Mon | Afternoon | SOCIAL | Daily automatic match (free): job running 1x/day via Supabase Edge Function | supabase/functions/match-diario/index.ts | Supabase Edge Functions (Deno); cron via pg_cron; push via Expo | 1h | ☐ | Haiku | schedule, gws-workflow, gws-workflow-weekly-digest, recipe-send-team-announcement, gws-chat-send, gws-gmail-send | Code
10d | Apr 13 Mon | Afternoon | SOCIAL | 'Request trade' button from profile → opens chat | src/app/perfil/[userId].tsx — botão que chama useChat.iniciarConversa() | Reuses logic from Day 7c; navigates to chat/[conversaId] | 2h | ☐ | Haiku | recipe-batch-invite-to-event, gws-chat-send, gws-gmail-send, persona-sales-ops | Code
11a | Apr 14 Tue | Morning | SOCIAL | Mandatory post-trade rating (1–5 stars + comment) | src/app/avaliacao/[conversaId].tsx, src/components/StarRating.tsx | Supabase trigger: when trade marked complete, sends push to rate | 3h | ☐ | Sonnet | frontend-design, gws-forms, recipe-collect-form-responses, gws-sheets-append, gws-chat-send | Code
11b | Apr 14 Tue | Morning | SOCIAL | Public reputation score + block new listings without rating | SQL trigger update avg_rating in profiles; src/hooks/useReputacao.ts | Supabase trigger on INSERT in avaliacoes; gate on create listing | 2h | ☐ | Haiku | recipe-log-deal-update, gws-sheets-append, gws-sheets, gws-workflow | Code
11c | Apr 14 Tue | Afternoon | SOCIAL | 'Trade didn't happen' button + report system + auto suspension | src/components/chat/BotaoReporte.tsx; tabela reportes; Supabase function check_suspensao | After 3 confirmed reports → flag is_suspended = true in profiles | 2h | ☐ | Haiku | frontend-design, recipe-create-gmail-filter, gws-chat-send, gws-gmail-send | Code
12a | Apr 15 Wed | Morning | PREMIUM | Integrate RevenueCat SDK (iOS + Android purchases) | src/lib/revenuecat.ts, src/hooks/usePremium.ts | react-native-purchases (RevenueCat); configure products in App Store Connect and Google Play | 3h | ☐ | Sonnet | gws-sheets, gws-docs, recipe-log-deal-update, persona-sales-ops | Code
12b | Apr 15 Wed | Morning | PREMIUM | Paywall: upgrade screen with plans ($4.99/month and $13.99 lifetime) | src/app/premium/paywall.tsx, src/components/premium/PlanoCard.tsx | RevenueCat Offerings API; error handling and restore purchase | 2h | ☐ | Sonnet | frontend-design, web-artifacts-builder, persona-sales-ops, canvas-design, gws-docs | Code
12c | Apr 15 Wed | Afternoon | PREMIUM | Premium feature gates at all critical app points | src/hooks/usePremium.ts — isPremium boolean usado em todo o app | HOC withPremiumGate or inline check + redirect to paywall | 1h | ☐ | Haiku | gws-sheets, recipe-log-deal-update, gws-workflow | Code
12d | Apr 15 Wed | Afternoon | PREMIUM | Integrate Google AdMob (banners for free users) | src/components/AdBanner.tsx; src/hooks/useAds.ts | react-native-google-mobile-ads; banner at bottom of search/feed screens | 1h | ☐ | Haiku | gws-sheets, gws-docs, recipe-log-deal-update | Code
13a | Apr 16 Thu | Morning | PREMIUM | Push notifications with Expo (token setup + send via Supabase) | src/lib/notifications.ts; supabase/functions/send-push/index.ts | expo-notifications; save token in profiles.expo_push_token | 3h | ☐ | Haiku | gws-workflow, gws-chat-send, gws-gmail-send, recipe-send-team-announcement | Code
13b | Apr 16 Thu | Morning | PREMIUM | Real-time automatic match (premium): Supabase trigger → Edge Function → push | supabase/functions/match-realtime/index.ts; trigger em itens_colecao on INSERT | Supabase Datebase Webhooks → Edge Function → Expo Push API | 2h | ☐ | Sonnet | schedule, gws-workflow, recipe-send-team-announcement, gws-chat-send, gws-gmail-send, gws-workflow-weekly-digest | Cowork
13c | Apr 16 Thu | Afternoon | PREMIUM | New chat message notification + badge on tab icon | src/hooks/useNotificacoes.ts; Realtime subscription em mensagens | expo-notifications + setBadgeCountAsync; unread count on tab icon | 2h | ☐ | Haiku | recipe-create-gmail-filter, gws-chat-send, gws-gmail-send, gws-workflow | Code
14a | Apr 17 Fri | Morning | LEGAL | Onboarding screen + location permission (GPS) with clear context | src/app/onboarding/index.tsx (3 slides); src/app/onboarding/permissoes.tsx | expo-location requestForegroundPermissionsAsync; AsyncStorage for onboarded flag | 2h | ☐ | Haiku | frontend-design, web-artifacts-builder, valyu-best-practices, gws-docs, recipe-create-doc-from-template | Code
14b | Apr 17 Fri | Morning | LEGAL | LGPD consent screen + privacy policy (external URL) | src/app/onboarding/lgpd.tsx; políticas em figurinhatrader.com.br/privacidade | WebBrowser.openBrowserAsync to open policy; required checkbox | 1h | ☐ | Haiku | frontend-design, docx, gws-docs, recipe-create-doc-from-template, gws-chat-send, canvas-design | Code
14c | Apr 17 Fri | Afternoon | LEGAL | Delete account and data (required by LGPD and App Store review) | src/app/configuracoes/excluir-conta.tsx; Supabase RPC delete_user_data(user_id) | RPC that cascades delete all user data; auth.admin.deleteUser | 1h | ☐ | Haiku | recipe-email-drive-link, gws-drive, recipe-find-large-files, gws-workflow | Code
14d | Apr 17 Fri | Afternoon | LEGAL | General settings: notifications, theme, change password, sign out | src/app/(tabs)/perfil/configuracoes.tsx | expo-notifications setNotificationHandler; AsyncStorage for preferences | 2h | ☐ | Haiku | frontend-design, gws-chat-send, recipe-create-feedback-form, gws-forms, gws-docs | Code
15a | Apr 18 Sat | Morning | POLISH | Testing on physical iPhone (iOS) and physical Android — identify crashes | Expo Go → TestFlight (iOS) and internal APK (Android) | expo run:ios + expo run:android; reportar crashes no terminal | 2h | ☐ | Haiku | webapp-testing, browser-use, playwright-skill, ios-simulator-skill, android-emulator-skill, valyu-best-practices | Manual
15b | Apr 18 Sat | Morning | POLISH | Loading skeletons, empty states and network error handling | src/components/ui/Skeleton.tsx, EmptyState.tsx, ErrorBoundary.tsx | react-native-reanimated for shimmer; try/catch with error toast | 3h | ☐ | Haiku | frontend-design, canvas-design, theme-factory, web-artifacts-builder | Code
15c | Apr 18 Sat | Afternoon | POLISH | Dark mode: system detection + application in design system | src/hooks/useColorScheme.ts; atualizar todas as cores em src/theme/ | useColorScheme from RN; Appearance API; global theme Context | 2h | ☐ | Sonnet | frontend-design, theme-factory, canvas-design, web-artifacts-builder | Code
15d | Apr 18 Sat | Afternoon | POLISH | Performance: memo on lists, lazy loading of images, reduce re-renders | FigurinhaCard, AnuncioCard, PerfilCard — todos com React.memo | React.memo, useMemo, useCallback where applicable; expo-image cache | 1h | ☐ | Sonnet | webapp-testing, browser-use, playwright-skill, valyu-best-practices, android-emulator-skill | Code
16a | Apr 19 Sun | Morning | STORES | App Store screenshots (iPhone 6.7") — minimum 3, ideal 8 | assets/screenshots/ios/*.png (1290×2796px) | Expo + iOS Simulator; screens: Map, Collection, Scan, Trades, Profile | 3h | ☐ | Haiku | canvas-design, browser-use, gws-drive-upload, recipe-bulk-download-folder | Manual
16b | Apr 19 Sun | Morning | STORES | App icon 1024×1024px no rounding + splash screen | assets/icon.png (1024×1024), assets/splash.png, app.json atualizado | Canva Pro or Figma; expo-splash-screen config | 1h | ☐ | Haiku | canvas-design, gws-drive-upload, gws-docs | Manual
16c | Apr 19 Sun | Afternoon | STORES | Store metadata: title, subtitle, description PT-BR + EN, keywords | docs/app-store-metadata.md — texto para App Store Connect e Google Play Console | Title: 'Figurinha Trader — World Cup 2026'; keywords: sticker trade album panini | 1h | ☐ | Haiku | docx, gws-docs, gws-sheets, recipe-backup-sheet-as-csv, recipe-generate-report-from-sheet, gws-drive-upload | Code
16d | Apr 19 Sun | Afternoon | STORES | EAS Build: generate production IPA (iOS) and AAB (Android) | eas.json configurado; executar eas build --platform all --profile production | Expo EAS Build; automatic certificates; wait ~30min | 2h | ☐ | Haiku | plugin-structure, gws-drive-upload, gws-docs, recipe-share-doc-and-notify | Code
16e | Apr 19 Sun | Afternoon | STORES | Test production builds on physical device before submitting | IPA via TestFlight interno; AAB via Google Play Internal Testing | Verify in-app purchases, permissions, push notifications in production | 1h | ☐ | Haiku | webapp-testing, browser-use, playwright-skill, ios-simulator-skill, android-emulator-skill, valyu-best-practices | Manual
17a | Apr 20 Mon | Morning | 🚀 SUBMIT | Submit to App Store Connect (iOS) | App Store Connect → New Version → upload IPA via Transporter or EAS Submit | eas submit --platform ios; select build; fill in 'What's New' | 2h | ☐ | Haiku | browser-use, gws-chat-send, gws-gmail-send, recipe-send-team-announcement, persona-sales-ops | Manual
17b | Apr 20 Mon | Morning | 🚀 SUBMIT | Submit to Google Play Console (Android) | Google Play Console → Production → New Release → upload AAB | eas submit --platform android; configure countries (start with Brazil) | 1h | ☐ | Haiku | browser-use, gws-chat-send, gws-gmail-send, recipe-send-team-announcement | Manual
17c | Apr 20 Mon | Afternoon | 🚀 SUBMIT | Activate Meta Ads campaign (pre-configured in Ads Manager) | Meta Ads Manager — campanha App Install já criada, ativar agora | Budget: R$800; targeting: Brazil, 16–45 years, interest in soccer + stickers | 30m | ☐ | Haiku | persona-sales-ops, gws-docs, gws-chat-send, recipe-send-team-announcement, gws-gmail-send, gws-sheets | Manual
17d | [6 empty] | 30m | ☐ | Haiku | - | Manual
ESTIMATED TOTAL — 17 days / ~105 hours of development | [6 empty] | 106h | ☐ 0/66

## N8N Workflows
Workflow ID | Name | Trigger | Actions | Frequency | Status
WF-001 | Daily EAS Build | Cron: 22:00 BRT | Run EAS build (Android) → Slack notify | Daily | Pending
WF-002 | Daily Tests | Cron: 08:00 BRT | Run Jest tests → Generate report → Slack notify | Daily | Pending
WF-003 | Weekly Report | Cron: Mon 09:00 | Fetch git commits → Generate summary → Slack | Weekly | Pending
WF-004 | Nightly Cleanup | Cron: 00:00 BRT | Delete old conversations, cache cleanup | Daily | Pending
WF-005 | Pre-Submit Check | Manual trigger | Full test suite → App Store validation → Report | On-demand | Pending
Workflow ID | Name | Trigger | Actions | Frequency | Status
WF-001 | Daily EAS Build | Cron: 22:00 BRT | Run EAS build (Android) → Slack notify | Daily | Pending
WF-002 | Daily Tests | Cron: 08:00 BRT | Run Jest tests → Generate report → Slack notify | Daily | Pending
WF-003 | Weekly Report | Cron: Mon 09:00 | Fetch git commits → Generate summary → Slack | Weekly | Pending
WF-004 | Nightly Cleanup | Cron: 00:00 BRT | Delete old conversations, cache cleanup | Daily | Pending
WF-005 | Pre-Submit Check | Manual trigger | Full test suite → App Store validation → Report | On-demand | Pending

## Composio Integration
Service | Toolkit | Functions | Cost | Status
Supabase | supabase | Create schema, run migrations, manage auth | Included in Composio | Connected
Vercel | vercel | Automatic deploy, CI/CD | Included in Composio | Connected
GitHub | github | Push commits, create PRs, manage branches | Included in Composio | Ready
Slack | slack | Send notifications, post reports | Included in Composio | Ready
Service | Toolkit | Functions | Cost | Status
Supabase | supabase | Create schema, run migrations, manage auth | Included in Composio | Connected
Vercel | vercel | Automatic deploy, CI/CD | Included in Composio | Connected
GitHub | github | Push commits, create PRs, manage branches | Included in Composio | Ready
Slack | slack | Send notifications, post reports | Included in Composio | Ready

## Custom Skills
Skill ID | Name | Input | Main Output | Status | Reusable?
SKL-001 | @react-native-generator | Component spec (name, props) | TypeScript .tsx file | Create | Yes (every time)
SKL-002 | @supabase-schema-generator | Table spec + RLS policy | SQL + RLS + .xlsx doc | Create | Yes (schemas)
SKL-003 | @test-automator | File/component path | Jest tests + coverage report | Create | Yes (tests)
Skill ID | Name | Input | Main Output | Status | Reusable?
SKL-001 | @react-native-generator | Component spec (name, props) | TypeScript .tsx file | Create | Yes (every time)
SKL-002 | @supabase-schema-generator | Table spec + RLS policy | SQL + RLS + .xlsx doc | Create | Yes (schemas)
SKL-003 | @test-automator | File/component path | Jest tests + coverage report | Create | Yes (tests)

## Database
FIGURINHA TRADER — Complete Datebase Schema (Supabase / PostgreSQL)
Table / Column | Tipo | Nullable? | PK/FK | Default | Description | RLS
PROFILES
id | uuid | NO | PK | auth.users.id | FK to auth.users | Owner read/write
username | text | NO | UNIQUE | — | @unique username in app | Everyone reads
full_name | text | YES | — | — | Full name | Everyone reads
avatar_url | text | YES | — | — | URL in Supabase Storage | Everyone reads
city | text | YES | — | — | User city | Everyone reads
lat | float8 | YES | — | — | Latitude (PostGIS) | Everyone reads
lng | float8 | YES | — | — | Longitude (PostGIS) | Everyone reads
is_premium | bool | NO | — | false | Updated by RevenueCat webhook | Owner read
avg_rating | numeric(3,2) | NO | — | 5.0 | Average of received ratings | Everyone reads
total_trocas | int4 | NO | — | 0 | Completed trades counter | Everyone reads
is_suspended | bool | NO | — | false | True after 3 confirmed reports | Owner read
expo_push_token | text | YES | — | — | Token for Expo notifications | Owner read/write
created_at | timestamptz | NO | — | now()
ALBUMS
id | uuid | NO | PK | gen_random_uuid()
nome | text | NO | — | — | Ex: 'Copa do Mundo 2026' | Everyone reads
ano | int4 | NO | — | — | Ano do álbum | Everyone reads
total_figurinhas | int4 | NO | — | — | Total de cromos (ex: 980) | Everyone reads
ativo | bool | NO | — | true | Exibir no app? | Everyone reads
FIGURINHAS
id | uuid | NO | PK | gen_random_uuid()
album_id | uuid | NO | FK→albums | — |  | Everyone reads
numero | int4 | NO | — | — | Número da figurinha (1–980) | Everyone reads
nome_jogador | text | YES | — | — | Player name ou tema | Everyone reads
pais | text | YES | — | — | País/seleção | Everyone reads
posicao | text | YES | — | — | GOL, ZAG, MEI, ATA, etc. | Everyone reads
is_especial | bool | NO | — | false | Figurinha brilhante/especial | Everyone reads
ITENS_COLECAO
id | uuid | NO | PK | gen_random_uuid()
user_id | uuid | NO | FK→profiles | — |  | Owner read/write
album_id | uuid | NO | FK→albums | — |  | Owner read/write
figurinha_id | uuid | NO | FK→figurinhas | — | UNIQUE(user_id,figurinha_id)
tem | bool | NO | — | false | Possui a figurinha? | Owner read/write
repetidas | int4 | NO | — | 0 | Quantas cópias extras tem | Owner read/write
WISHLIST
user_id | uuid | NO | FK→profiles PK | — | Composta com figurinha_id | Everyone reads
figurinha_id | uuid | NO | FK→figurinhas PK | — |  | Everyone reads
created_at | timestamptz | NO | — | now()
ANUNCIOS
id | uuid | NO | PK | gen_random_uuid()
user_id | uuid | NO | FK→profiles | — | Dono do anúncio | Everyone reads
figurinha_id | uuid | NO | FK→figurinhas | — | Figurinha ofertada | Everyone reads
descricao | text | YES | — | — | Observação livre | Everyone reads
is_premium | bool | NO | — | false | Aparece primeiro na busca | Everyone reads
ativo | bool | NO | — | true | Anúncio visível? | Everyone reads
created_at | timestamptz | NO | — | now()
CONVERSAS
id | uuid | NO | PK | gen_random_uuid()
user1_id | uuid | NO | FK→profiles | — | UNIQUE(user1_id,user2_id) | Partes da conversa
user2_id | uuid | NO | FK→profiles | — |  | Partes da conversa
anuncio_id | uuid | YES | FK→anuncios | — | Anúncio de origem (opcional)
ultima_mensagem_at | timestamptz | YES | — | — | Para ordenar lista de chats
MENSAGENS
id | uuid | NO | PK | gen_random_uuid()
conversa_id | uuid | NO | FK→conversas | — |  | Partes da conversa
sender_id | uuid | NO | FK→profiles | — |  | Partes da conversa
texto | text | NO | — | — | Conteúdo da mensagem
lida | bool | NO | — | false
created_at | timestamptz | NO | — | now()
ENCONTROS
id | uuid | NO | PK | gen_random_uuid()
criador_id | uuid | NO | FK→profiles | — | Deve ser premium | Everyone reads
titulo | text | NO | — | — | Ex: 'Troca na Praça Osório' | Everyone reads
endereco | text | NO | — | — | Text address | Everyone reads
lat | float8 | NO | — | — | Coordenada para o mapa | Everyone reads
lng | float8 | NO | — | — | Coordenada para o mapa | Everyone reads
data_hora | timestamptz | NO | — | — | Date e hora do encontro | Everyone reads
capacidade_max | int4 | YES | — | — | Limite de confirmados (opcional) | Everyone reads
ativo | bool | NO | — | true | Exibir no mapa? | Everyone reads
CONFIRMACOES_ENCONTRO
encontro_id | uuid | NO | FK→encontros PK | — | Composta com user_id | Everyone reads
user_id | uuid | NO | FK→profiles PK | — |  | Owner read/write
created_at | timestamptz | NO | — | now()
AVALIACOES
id | uuid | NO | PK | gen_random_uuid()
avaliador_id | uuid | NO | FK→profiles | — | Quem avaliou | Everyone reads
avaliado_id | uuid | NO | FK→profiles | — | Quem foi avaliado | Everyone reads
conversa_id | uuid | NO | FK→conversas | — | Origem da avaliação
nota | int2 | NO | — | — | 1 a 5 | Everyone reads
comentario | text | YES | — | — | Comentário livre | Everyone reads
created_at | timestamptz | NO | — | now()
PINS_VERIFICADOS
id | uuid | NO | PK | gen_random_uuid()
nome | text | NO | — | — | Name da loja | Everyone reads
endereco | text | NO | — | — | Endereço completo | Everyone reads
lat | float8 | NO | — | — |  | Everyone reads
lng | float8 | NO | — | — |  | Everyone reads
foto_url | text | YES | — | — | Foto da loja | Everyone reads
horario | text | YES | — | — | Ex: 'Seg-Sex 9h–18h' | Everyone reads
plano | text | NO | — | basico | 'basico' ou 'completo'
ativo | bool | NO | — | true |  | Everyone reads
valido_ate | date | NO | — | — | Date de vencimento do plano

## Screens & Navigation
FIGURINHA TRADER — Screen and Component Tree (expo-router)
Route (expo-router) | Main Components | API Calls (Supabase) | Tier | Sprint
AUTH
app/_layout.tsx | SplashScreen, AuthProvider, ThemeProvider | auth.onAuthStateChange() | Todos | Day 3
app/(auth)/login.tsx | LoginForm, GoogleButton, AppleButton, SocialDivider | supabase.auth.signInWithPassword() / OAuth | Todos | Day 3
app/(auth)/cadastro.tsx | CadastroForm, PasswordStrength | supabase.auth.signUp() | Todos | Day 3
app/onboarding/index.tsx | OnboardingSlide x3, ProgressDots | AsyncStorage.setItem('onboarded') | Todos | Day 14
app/onboarding/permissoes.tsx | PermissaoCard (localização), PermissaoCard (notificações) | expo-location.requestPermission(), expo-notifications.requestPermission() | Todos | Day 14
app/onboarding/lgpd.tsx | LGPDCheckbox, PrivacidadeLink | AsyncStorage.setItem('lgpd_aceito') | Todos | Day 14
TAB: COLLECTION
app/(tabs)/colecao/index.tsx | ColecaoProgress, FigurinhaGrid (FlashList), FiltroBar, SearchInput | SELECT itens_colecao WHERE user_id = me | Todos | Day 4
app/(tabs)/colecao/scan.tsx | Camera (VisionCamera), ScanOverlay, FigurinhaConfirmCard, LimiteCounter | INSERT/UPSERT itens_colecao; INSERT scan_logs | Free(lim)/Prem | Day 5
app/(tabs)/colecao/pacote.tsx | PacoteCounter, FigurinhaSwipeStack, BatchConfirmButton | UPSERT itens_colecao (batch 7 itens) | Todos | Day 5
app/(tabs)/colecao/stats.tsx | StatCard (% completo, faltam X, repetidas), ProgressBar | COUNT(*) GROUP BY tem em itens_colecao | Todos | Day 4
TAB: TRADES
app/(tabs)/trocas/index.tsx | AnuncioFeed (FlashList), SearchBar, FiltroModal, FeaturedBadge | SELECT anuncios JOIN figurinhas ORDER BY is_premium DESC | Todos | Day 6
app/(tabs)/trocas/novo.tsx | FigurinhaSelector, DescricaoInput, PreviewCard, PublicarButton | INSERT anuncios | Todos | Day 6
app/(tabs)/trocas/wishlist.tsx | FigurinhaGrid (somente faltam), HeartButton | SELECT wishlist WHERE user_id = me; DELETE/INSERT wishlist | Todos | Day 6
app/(tabs)/trocas/mensagens.tsx | ConversaList (FlashList), UnreadBadge, SearchConversas | SELECT conversas JOIN profiles ORDER BY ultima_mensagem_at | Todos | Day 7
app/chat/[conversaId].tsx | MessageBubble, InputBar, AnexoButton, AvaliarButton | SELECT mensagens (Realtime); INSERT mensagens | Todos | Day 7
app/avaliacao/[conversaId].tsx | StarRating, ComentarioInput, EnviarButton | INSERT avaliacoes; RPC atualiza avg_rating em profiles | Todos | Day 11
TAB: SEARCH
app/(tabs)/busca/index.tsx | SearchInput (debounce 300ms), PerfilCard (FlashList), TabsSelector | SELECT profiles WHERE username ILIKE '%q%' | Todos | Day 8
app/(tabs)/busca/por-figurinha.tsx | FigurinhaSearchInput, PerfilCard com badge 'Tem esta' | SELECT profiles JOIN itens_colecao WHERE fig_id = X AND tem = true | Todos | Day 8
app/(tabs)/busca/por-localizacao.tsx | MapaPreview, RaioSlider (premium), PerfilCard | SELECT profiles WHERE ST_DWithin(location, me, raio_km) | Free+Prem | Day 8
app/(tabs)/busca/sugestoes.tsx | CompatibilidadeCard (% de match), SolicitarButton | RPC match_bilateral(user_id) retorna top 20 matches | Premium | Day 8
app/(tabs)/busca/ranking.tsx | RankingCard com posição, %, total trocas | SELECT VIEW ranking_usuarios ORDER BY pct DESC LIMIT 100 | Todos | Day 10
TAB: MAP
app/(tabs)/mapa/index.tsx | MapLibreView, PinEncontro, PinVerificado, FiltrosMapa, UserLocationDot | SELECT encontros (ativo=true, data >= hoje); SELECT pins_verificados | Todos | Day 9
app/(tabs)/mapa/novo-encontro.tsx | EnderecoInput (OpenCage autocomplete), DateHoraPicker, CapacidadeInput | INSERT encontros | Premium | Day 9
app/(tabs)/mapa/encontro/[id].tsx | EncontroHeader, MapaStatic, ConfirmadosCount, ListaConfirmados, VouComparecerButton | SELECT encontros; SELECT confirmacoes; INSERT/DELETE confirmacoes | Todos | Day 9
TAB: PROFILE
app/(tabs)/perfil/index.tsx | PerfilHeader (avatar, nome, stats), ColecaoMiniProgress, WishlistPreview, AnunciosAtivos | SELECT profiles; SELECT itens_colecao stats; SELECT anuncios | Todos | Day 10
app/perfil/[userId].tsx | PerfilHeader, StarsRating, TrocasCount, WishlistPublica, AnunciosList, SolicitarTrocaButton | SELECT profiles WHERE id = userId (público) | Todos | Day 10
app/(tabs)/perfil/configuracoes.tsx | NotifToggle, TemaToggle, AlterarSenhaButton, ExcluirContaButton, SairButton | auth.signOut(); RPC delete_user_data() | Todos | Day 14
app/(tabs)/perfil/premium/paywall.tsx | PlanoCard x2, FeatureList, ComprarButton, RestoreButton | RevenueCat.purchasePackage(); RestorePurchases() | Todos | Day 12
MODAIS & OUTROS
src/components/PremiumGate.tsx | Modal com prévia da feature + botão 'Ver planos' | usePremium() hook | Todos | Day 12
src/components/ui/Toast.tsx | Mensagem flutuante (sucesso/erro/info) | — | Todos | Day 3
src/components/ui/BottomSheet.tsx | Modal de fundo deslizante (filtros, opções) | — | Todos | Day 3
src/components/ui/Skeleton.tsx | Loading placeholder animado | — | Todos | Day 15
src/components/ui/EmptyState.tsx | Ilustração + texto para listas vazias | — | Todos | Day 15

## Dependencies & Setup
FIGURINHA TRADER — Dependencies, Environment Variables, and Setup
Package / Variable | Version / Value | Cost | Purpose
CORE NPM DEPENDENCIES
expo | ~52.x | Free | App base runtime
expo-router | ~4.x | Free | File-based navigation (like Next.js)
react-native | 0.76.x | Free | Mobile framework
@supabase/supabase-js | ^2.x | Free | Supabase client (auth, database, storage, realtime)
zustand | ^5.x | Free | Global state management (lightweight, no boilerplate)
react-hook-form | ^7.x | Free | Forms with performant validation
zod | ^3.x | Free | Schema validation (integrates with react-hook-form)
@shopify/flash-list | ^1.x | Free | Performant FlatList for long lists
expo-image | ^2.x | Free | Imagens com cache inteligente
MAPA
@maplibre/maplibre-react-native | ^10.x | Free | Renderização de mapas vetoriais
expo-location | ^17.x | Free | GPS do dispositivo (permissão obrigatória)
TILES: openfreemap.org | — | Free (sem limite) | Estilo: liberty — URL: tiles.openfreemap.org/styles/liberty
OpenCage Geocoding API | — | Free (2.500/dia) | Converter endereço texto em lat/lng
CÂMERA E IA
react-native-vision-camera | ^4.x | Free | Câmera de alta performance para scan
@react-native-ml-kit/text-recognition | ^3.x | Free (on-device) | Reconhecer número da figurinha pela câmera
PREMIUM E ADS
react-native-purchases | ^8.x | Free (RevenueCat cobra % sobre receita) | Assinaturas in-app (iOS + Android unificado)
react-native-google-mobile-ads | ^14.x | Free (Google paga você) | AdMob banners e interstitials para free users
NOTIFICAÇÕES
expo-notifications | ^0.29.x | Free | Push notifications nativas iOS + Android
expo-device | ^6.x | Free | Detectar se é simulador (não registrar push em sim)
UTILITÁRIOS
expo-auth-session | ^6.x | Free | OAuth flows (Google, Apple)
expo-crypto | ^13.x | Free | Hashing para segurança
expo-web-browser | ^14.x | Free | Abrir links externos (política de privacidade)
@react-native-async-storage/async-storage | ^2.x | Free | Armazenamento local (onboarding flag, preferências)
react-native-reanimated | ^3.x | Free | Animações performáticas (skeleton, transições)
BUILD & DEPLOY
eas-cli (Expo EAS) | latest | Free (30 builds/mês) | Build de produção IPA e AAB
ENVIRONMENT VARIABLES (.env)
EXPO_PUBLIC_SUPABASE_URL | https://xxx.supabase.co | — | URL do projeto Supabase
EXPO_PUBLIC_SUPABASE_ANON_KEY | eyJ... | — | Chave pública anon Supabase
SUPABASE_SERVICE_ROLE_KEY | eyJ... | — | Chave service role (NUNCA no cliente!)
EXPO_PUBLIC_OPENCAGE_KEY | abc123... | — | Chave OpenCage Geocoding
EXPO_PUBLIC_ADMOB_BANNER_ID_IOS | ca-app-pub-xxx | — | ID do banner AdMob iOS
EXPO_PUBLIC_ADMOB_BANNER_ID_ANDROID | ca-app-pub-xxx | — | ID do banner AdMob Android
REVENUECAT_API_KEY_IOS | appl_xxx | — | Chave RevenueCat iOS
REVENUECAT_API_KEY_ANDROID | goog_xxx | — | Chave RevenueCat Android
EXTERNAL SERVICES — SETUP NECESSÁRIO
Supabase | supabase.com | Free | Create projeto, habilitar Auth providers, habilitar PostGIS extension
RevenueCat | revenuecat.com | Free até escalar | Create app iOS + Android, configurar produtos, webhook para atualizar is_premium
Google AdMob | admob.google.com | Free (você recebe) | Create app, gerar IDs de banner e interstitial
OpenCage | opencagedata.com | Free (2.500/dia) | Create conta, copiar API key
OpenFreeMap | openfreemap.org | Free (sem limite) | Sem cadastro necessário — só usar a URL dos tiles
Expo EAS | expo.dev | Free | Create conta Expo, configurar eas.json
Apple Developer | developer.apple.com | US$ 99/ano | Create conta, configurar bundle ID: com.figurinhatrader.app
Google Play Console | play.google.com/console | US$ 25 único | Create conta, configurar app: br.com.figurinhatrader

## Skills Mapping
SKILLS MAPPING — 58 MAPPED SKILLS
Task ID | Task Name | Skills (58 Unique)
1a | Create Expo project with TypeScript | plugin-structure, command-development, agent-development, mcp-integration, gws-drive
1b | Configure GitHub repo and folder structure | plugin-structure, gws-drive, gws-docs, recipe-organize-drive-folder
1c | Create projeto Supabase (free tier) e configurar .e | gws-drive, gws-docs, mcp-integration, recipe-create-shared-drive
1d | Create Apple Developer account + Google Play Console | gws-chat-send, gws-gmail-send, recipe-send-team-announcement
1e | Install core project dependencies | gws-sheets, recipe-create-task-list, recipe-review-overdue-tasks
1f | Configurar ocloud (Oracle Cloud Always Free) — pro | schedule, gws-workflow, mcp-integration, recipe-create-task-list, gws-chat-send, agent-development
2a | Create tabelas do banco: profiles, albums, figurinh | docx, gws-docs, gws-sheets, recipe-generate-report-from-sheet, recipe-backup-sheet-as-csv
2b | Create tables: colecoes, itens_colecao, wishlist | docx, gws-docs, gws-sheets, recipe-generate-report-from-sheet
2c | Create tables: anuncios, conversas, mensagens | docx, gws-docs, recipe-generate-report-from-sheet
2d | Create tabelas: encontros, confirmacoes, avaliacoes | docx, gws-docs, recipe-generate-report-from-sheet, gws-drive-upload
3a | Configurar autenticação: Email, Google OAuth, Appl | gws-drive, gws-docs, docx, plugin-structure
3b | Create Design System: cores, tipografia, espaçament | canvas-design, frontend-design, theme-factory, excalidraw-diagram, gws-docs, recipe-create-presentation, gws-sheets, valyu-best-practices
3c | Create componentes base: Button, Input, Card, Avata | frontend-design, web-artifacts-builder, theme-factory, canvas-design, valyu-best-practices, recipe-create-presentation
3d | Configure navigation: Bottom Tabs + Stack per tab | frontend-design, web-artifacts-builder, canvas-design, excalidraw-diagram
4a | Collection screen: sticker list with filters | frontend-design, web-artifacts-builder, claude-d3js-skill, canvas-design, recipe-create-presentation
4b | Logic to mark have/missing/duplicate with quantity | gws-sheets, recipe-log-deal-update, gws-workflow
4c | Barra de progresso e estatísticas básicas (% compl | frontend-design, claude-d3js-skill, canvas-design, gws-sheets-append
5a | Implementar scan por IA com Google ML Kit (reconhe | webapp-testing, browser-use, playwright-skill, gws-forms, recipe-collect-form-responses
5b | Modo pacote aberto: registrar 7 figurinhas em sequ | frontend-design, web-artifacts-builder, canvas-design, gws-docs
5c | Gate de limite free (30 scans/dia): contador diári | gws-sheets, recipe-log-deal-update, gws-workflow
6a | Create trade listing screen | frontend-design, web-artifacts-builder, persona-sales-ops, gws-forms, gws-docs, recipe-email-drive-link
6b | Listings feed with search by number/player/country | frontend-design, web-artifacts-builder, recipe-email-drive-link, gws-drive-upload, claude-d3js-skill, persona-sales-ops
6c | Badge de destaque para anúncios premium (ordenação | canvas-design, theme-factory, gws-docs
6d | Wishlist: adicionar/remover figurinhas desejadas, | frontend-design, recipe-create-task-list, gws-tasks, gws-chat-send
7a | Real-time chat: conversation screen | frontend-design, web-artifacts-builder, gws-chat-send, gws-chat, gws-gmail, recipe-create-gmail-filter
7b | Active conversations list | frontend-design, web-artifacts-builder, gws-chat, gws-chat-send
7c | Start conversation from a listing | recipe-create-gmail-filter, recipe-label-and-archive-emails, gws-gmail-watch, gws-workflow
8a | Profile search by name/@username | frontend-design, web-artifacts-builder, gws-people, gws-sheets-read, persona-exec-assistant
8b | Sticker search: 'who has #347?' | frontend-design, web-artifacts-builder, claude-d3js-skill, gws-sheets, recipe-generate-report-from-sheet
8c | Busca por localização (raio em km, free=cidade, pr | frontend-design, web-artifacts-builder, gws-drive, gws-sheets, recipe-find-large-files
8d | Sugestão automática de perfis compatíveis (match b | gws-sheets, recipe-log-deal-update, persona-sales-ops
9a | Tela de mapa com OpenFreeMap + MapLibre React Nati | frontend-design, web-artifacts-builder, excalidraw-diagram, canvas-design, gws-sheets
9b | Pins de encontros no mapa (azul=user, dourado=esta | canvas-design, theme-factory, gws-drive-upload
9c | Create ponto de encontro (apenas premium): form com | frontend-design, recipe-schedule-recurring-event, gws-calendar-insert, gws-calendar, gws-docs
9d | Botão 'Vou comparecer' + lista de confirmados (pre | recipe-batch-invite-to-event, gws-calendar-insert, gws-calendar, gws-chat-send, gws-gmail-send
10a | Public profile screen (own + others) | frontend-design, web-artifacts-builder, persona-exec-assistant, gws-people, gws-sheets-read, canvas-design
10b | Ranking de colecionadores por cidade (% completo + | frontend-design, claude-d3js-skill, recipe-generate-report-from-sheet, gws-sheets, gws-sheets-read, persona-sales-ops
10c | Match automático diário (free): job que roda 1x/di | schedule, gws-workflow, gws-workflow-weekly-digest, recipe-send-team-announcement, gws-chat-send, gws-gmail-send
10d | Botão 'Solicitar troca' direto do perfil → abre ch | recipe-batch-invite-to-event, gws-chat-send, gws-gmail-send, persona-sales-ops
11a | Avaliação pós-troca obrigatória (1–5 estrelas + co | frontend-design, gws-forms, recipe-collect-form-responses, gws-sheets-append, gws-chat-send
11b | Score de reputação público + bloqueio de novos anú | recipe-log-deal-update, gws-sheets-append, gws-sheets, gws-workflow
11c | Botão 'Troca não aconteceu' + sistema de reporte + | frontend-design, recipe-create-gmail-filter, gws-chat-send, gws-gmail-send
12a | Integrate RevenueCat SDK (iOS + Android purchases) | gws-sheets, gws-docs, recipe-log-deal-update, persona-sales-ops
12b | Paywall: tela de upgrade com planos (R$14,90/mês e | frontend-design, web-artifacts-builder, persona-sales-ops, canvas-design, gws-docs
12c | Feature gates premium em todos os pontos críticos | gws-sheets, recipe-log-deal-update, gws-workflow
12d | Integrate Google AdMob (banners for free users) | gws-sheets, gws-docs, recipe-log-deal-update
13a | Notificações push com Expo (setup de tokens + envi | gws-workflow, gws-chat-send, gws-gmail-send, recipe-send-team-announcement
13b | Match automático em tempo real (premium): trigger | schedule, gws-workflow, recipe-send-team-announcement, gws-chat-send, gws-gmail-send, gws-workflow-weekly-digest
13c | Notificação de nova mensagem no chat + badge no íc | recipe-create-gmail-filter, gws-chat-send, gws-gmail-send, gws-workflow
14a | Tela de onboarding + permissão de localização (GPS | frontend-design, web-artifacts-builder, valyu-best-practices, gws-docs, recipe-create-doc-from-template
14b | Tela de consentimento LGPD + política de privacida | frontend-design, docx, gws-docs, recipe-create-doc-from-template, gws-chat-send, canvas-design
14c | Excluir conta e dados (obrigatório LGPD e App Stor | recipe-email-drive-link, gws-drive, recipe-find-large-files, gws-workflow
14d | Configurações gerais: notificações, tema, alterar | frontend-design, gws-chat-send, recipe-create-feedback-form, gws-forms, gws-docs
15a | Testes em iPhone físico (iOS) e Android físico — i | webapp-testing, browser-use, playwright-skill, ios-simulator-skill, android-emulator-skill, valyu-best-practices
15b | Loading skeletons, empty states e tratamento de er | frontend-design, canvas-design, theme-factory, web-artifacts-builder
15c | Dark mode: detecção do sistema + aplicação no desi | frontend-design, theme-factory, canvas-design, web-artifacts-builder
15d | Performance: memo em listas, lazy loading de image | webapp-testing, browser-use, playwright-skill, valyu-best-practices, android-emulator-skill
16a | Screenshots para App Store (iPhone 6.7") — mínimo | canvas-design, browser-use, gws-drive-upload, recipe-bulk-download-folder
16b | Ícone do app 1024×1024px sem arredondamento + spla | canvas-design, gws-drive-upload, gws-docs
16c | Metadata das lojas: título, subtítulo, descrição P | docx, gws-docs, gws-sheets, recipe-backup-sheet-as-csv, recipe-generate-report-from-sheet, gws-drive-upload
16d | EAS Build: gerar IPA (iOS) e AAB (Android) de prod | plugin-structure, gws-drive-upload, gws-docs, recipe-share-doc-and-notify
16e | Testar builds de produção em dispositivo físico an | webapp-testing, browser-use, playwright-skill, ios-simulator-skill, android-emulator-skill, valyu-best-practices
17a | Submit to App Store Connect (iOS) | browser-use, gws-chat-send, gws-gmail-send, recipe-send-team-announcement, persona-sales-ops
17b | Submit to Google Play Console (Android) | browser-use, gws-chat-send, gws-gmail-send, recipe-send-team-announcement
17c | Ativar campanha Meta Ads (pré-configurada no Ads M | persona-sales-ops, gws-docs, gws-chat-send, recipe-send-team-announcement, gws-gmail-send, gws-sheets
17d |  | -
ESTIMATED TOTAL — 17 days / ~105 hours of development |  | -